## Instructions
Findings review trail
Purpose | One row per finding. Each role completes its own column group in order; the Stage, Waiting on and Disposition columns update on their own. A finding counts as decided only when its Stage is Closed.
Order | 1. Identity Engineer drafts the finding with evidence (blue). 2. Identity Architect assesses and proposes the solution (green). 3. Zero Trust Architect confirms alignment and maturity (purple). 4. Client decision authority decides (orange).
Which cells to edit | Only the shaded cells in your own column group on the Review Trail sheet. Columns with a dropdown accept list values only. Hover over a column header for what goes in it. Do not edit the grey Disposition formulas, except Tracking ID.
Stage logic | Draft = Engineer section only. Architect reviewed = Architect severity set. With client = Alignment set. Closed = Client decision set.
After the decision | Accept and remediate -> Jira story on the remediation backlog. Accept risk -> exception register (owner, expiry, compensating control). Defer -> status register (owner, risk, disposition, follow-on, target date). Reject -> record the rationale. Put the resulting ID in Tracking ID.
Evidence | Each finding links to its evidence note (findings\F-xx.md) in the approved evidence location: run folder, file SHA-256, run account, data-as-of time and the closure test. Never paste names or account details into this workbook.
Gaps sheet | Everything that is a gap but not a counted finding: Control (a theme that groups findings), Capability (a process or tool that is missing, often raised in a meeting), Evidence (could not be assessed yet: access, inputs), Coverage (nothing measures it) and Decision (waiting on a decision). Link gaps to findings by ID; do not copy findings onto it. Close an Evidence gap when the run lands; it may then produce findings.
Definitions | Severity scale, Zero Trust maturity levels, pillars, decisions and gap types: see the Definitions sheet.
Example row (illustrative) | ID F-EX ¦ Finding: security groups with no accountable owner ¦ Source: 05 ad-groups.csv, OwnerStatus not OK ¦ Count 42 of 310 ¦ Observed severity Low ¦ Architect severity Low; root cause: no owner field in the group request form; solution: make owner mandatory in the request form and assign owners for existing groups; effort M; gate G3 ¦ ZT pillar Governance, Use least privilege, Initial -> Advanced, Aligned ¦ Client decision Accept and remediate -> Remediation backlog (Jira story).
Colour key
Engineer finding | Completed by: Identity Engineer
Architect assessment and solution | Completed by: Identity Architect
Zero Trust alignment | Completed by: Zero Trust Architect
Client response | Completed by: Client decision authority
Disposition | Completed by: Calculated / tracking

## Summary
Findings review trail
Counts update as the Review Trail is filled in. As of: template
Stage | Findings
Draft
Architect reviewed
With client
Closed
Total
Observed severity | Findings
Critical
High
Medium
Low
Total
Architect severity | Findings
Critical
High
Medium
Low
Total
Client decision | Findings
Accept and remediate
Accept risk
Defer
Reject
Total
Zero Trust pillar | Findings
Identity
Devices
Networks
Applications and workloads
Data
Visibility and analytics
Automation and orchestration
Governance
Total
Gap type | Gaps
Control
Capability
Evidence
Coverage
Decision
Total
Gap status | Gaps
Open
In progress
Closed
Accepted
Total

## Review Trail
Engineer finding (Identity Engineer) | [10 empty] | Architect assessment and solution (Identity Architect) | [7 empty] | Zero Trust alignment (Zero Trust Architect) | [7 empty] | Client response (Client decision authority) |  |  |  | Disposition (Calculated / tracking)
ID | Finding | Source and filter | Count | Population | Observed severity | HITRUST CSF | Proposed ZT pillar / principle | Initial recommendation | Evidence note | Engineer date | Architect severity | Root cause | Proposed solution | Effort | Dependencies | Target gate / sprint | Architect | Architect date | ZT pillar | ZT principle | Current maturity | Target maturity | Alignment | ZT comment | ZT Architect | ZT date | Client decision | Decided by | Decision date | Client comment | Stage | Waiting on | Disposition | Tracking ID
Note on A2: Finding ID, F-01 onward
Note on B2: What was observed, in one line
Note on C2: Script, file and filter or summary metric that produced the count
Note on D2: Observed count
Note on E2: What the count is out of (the denominator)
Note on F2: Critical / High / Medium / Low, per the Definitions sheet
Note on G2: HITRUST CSF control reference
Note on H2: Engineer's proposal; the Zero Trust Architect confirms
Note on I2: Engineer's first recommendation; the Architect owns the solution
Note on J2: Evidence note in the evidence location (findings\F-xx.md): run folder, SHA-256, run account, closure test
Note on K2: Date the finding was drafted
Note on L2: Agree or adjust the observed severity
Note on M2: Why this exists (process, design, tooling, ownership)
Note on N2: What to change, at the level a change record can be built from
Note on O2: S / M / L / XL
Note on P2: Access, decisions, other findings or platforms this depends on
Note on Q2: SOW gate (G1-G5) or sprint
Note on R2: Reviewer (role or name)
Note on S2: Date reviewed
Note on T2: CISA Zero Trust Maturity Model pillar or cross-cutting capability
Note on U2: Verify explicitly / Use least privilege / Assume breach
Note on V2: Traditional / Initial / Advanced / Optimal
Note on W2: Maturity the solution reaches
Note on X2: Does the proposed solution fit the target Zero Trust design?
Note on Y2: Changes needed for alignment, or why not aligned
Note on Z2: Reviewer (role or name)
Note on AA2: Date reviewed
Note on AB2: Accept and remediate / Accept risk / Defer / Reject
Note on AC2: Client decision authority (role or name)
Note on AD2: Date of the decision
Note on AE2: Conditions, rationale, or reason for risk acceptance, deferral or rejection
Note on AF2: Calculated from which sections are complete
Note on AG2: Calculated: who acts next
Note on AH2: Calculated from the client decision: where the finding goes next
Note on AI2: Jira story, exception register ID or status register ID

## Gaps
Gap register (control, capability, evidence, coverage and decision gaps; findings stay on the Review Trail)
ID | Type | Gap | Area | Current state | Target state | Impact | Priority | Related findings | Source | Owner | Status | Next step | Raised
Note on A2: Gap ID, G-01 onward
Note on B2: Control = environment falls short (theme over findings); Capability = process or tool missing; Evidence = could not be assessed yet; Coverage = nothing measures it; Decision = waiting on a decision
Note on C2: The gap, in one line
Note on D2: Zero Trust pillar or domain
Note on E2: What is in place today
Note on F2: What closes the gap
Note on G2: What the gap puts at risk, or what it blocks
Note on H2: High / Medium / Low
Note on I2: Finding IDs on the Review Trail
Note on J2: Script and run, finding, or meeting and date where it was raised
Note on K2: Role that closes it
Note on L2: Open / In progress / Closed / Accepted
Note on M2: Next action, or why it was accepted
Note on N2: Date raised

## Definitions
Severity
Critical | Reaches Tier 0 (domain or tenant control), or leaves a leaver or an admin with no second factor. Fix or formally accept within the current sprint.
High | Privileged access held outside the intended model, or a gap that affects many accounts. Plan in the next sprint.
Medium | Hygiene gap with limited reach, or one that another control partly covers. Schedule in the remediation backlog.
Low | Housekeeping: naming, ownership records, clean-up of unused objects. Batch with routine work.
Zero Trust maturity (CISA ZTMM v2.0)
Traditional | Manual, static configuration; siloed enforcement; limited visibility.
Initial | Starting automation of attribute assignment and response; some cross-pillar integration.
Advanced | Automated controls and centralized visibility across pillars; policies based on cross-pillar inputs.
Optimal | Fully automated, just-in-time lifecycles and dynamic policies with continuous monitoring.
Zero Trust principles
Verify explicitly | Authenticate and authorize on every request using all available signals.
Use least privilege | Just-in-time and just-enough access; risk-based adaptive policies.
Assume breach | Minimize blast radius, segment access, verify end to end, monitor.
Client decision
Accept and remediate | The client accepts the finding and the proposed solution; it goes to the remediation backlog.
Accept risk | The client accepts the residual risk without remediation; recorded in the exception register with owner, compensating control and expiry.
Defer | Valid finding, not addressed in this phase; recorded in the status register with owner, risk, disposition, follow-on and target date. Never represented as implemented.
Reject | The client does not accept the finding; the rationale is recorded.
Gap type
Control | The environment falls short of the target; groups the findings that show it.
Capability | A process, tool or function that does not exist or is not used (for example no access review process, licensed feature unused).
Evidence | Not assessed yet because access, an export or an input is missing. Never read as a clean result.
Coverage | Asked for by the scope but not measured by any script; needs another source.
Decision | Work is waiting on a decision (platform direction, ownership, scope).
Source | Severity scale: engagement register instructions. Maturity levels and pillars: CISA Zero Trust Maturity Model v2.0 (April 2023), https://www.cisa.gov/zero-trust-maturity-model

## Lists (hidden)
Severity | Effort | Gate | Pillar | Principle | Maturity | Alignment | Decision | GapType | GapStatus | Priority
Critical | S | G0 Pre-project | Identity | Verify explicitly | Traditional | Aligned | Accept and remediate | Control | Open | High
High | M | G1 | Devices | Use least privilege | Initial | Aligned with changes | Accept risk | Capability | In progress | Medium
Medium | L | G2 | Networks | Assume breach | Advanced | Not aligned | Defer | Evidence | Closed | Low
Low | XL | G3 | Applications and workloads |  | Optimal |  | Reject | Coverage | Accepted
|  | G4 | Data |  |  |  |  | Decision
|  | G5 | Visibility and analytics
|  | Follow-on | Automation and orchestration
Governance